# AI Patient Follow-Up Assistant — Project Plan

Sep 24, 2026 · @Muthuselvam M

The working app — three agents, RAG, Streamlit UI, deployed on AWS EC2 — is delivered and demoed by Oct 3, 2026, in seven modules over eight working days.

## Milestones

Work runs Thu Sep 24 to Fri Oct 2, with Sat Oct 3 for final checks and the demo; Sat–Sun Sep 26–27 is buffer.

| # | Module | Start | End | Deliverable |
| --- | --- | --- | --- | --- |
| M1 | Setup and synthetic data | Sep 24 | Sep 25 | Repo, Docker skeleton, 100 synthetic patients in S3 |
| M2 | RAG and vector store | Sep 25 | Sep 28 | ChromaDB/FAISS index and a working retriever |
| M3 | Agents | Sep 28 | Sep 29 | Summary, Reminder and Escalation agents, each tested alone |
| M4 | Workflow and memory | Sep 29 | Sep 30 | Sequential LangGraph pipeline with short- and long-term memory |
| M5 | Streamlit frontend | Sep 30 | Oct 1 | Dashboard: run follow-ups, view summaries, reminders, alerts |
| M6 | AWS deployment | Oct 1 | Oct 2 | App running on EC2 in Docker, reading and writing S3 |
| M7 | Testing, docs and demo | Oct 2 | Oct 3 | Test report, README, architecture doc, live demo |

## Tasks

| ID | Module | Task | Due | Depends on | Done when |
| --- | --- | --- | --- | --- | --- |
| T1.1 | M1 | Create repo, folder structure, requirements.txt, Dockerfile | Sep 24 | — | Container builds and runs locally |
| T1.2 | M1 | Set up AWS account access: EC2 key pair, S3 bucket, IAM role | Sep 24 | — | Bucket reachable from local code |
| T1.3 | M1 | Define patient data schema (demographics, discharge, meds, appointments, responses) | Sep 24 | — | Schema JSON reviewed |
| T1.4 | M1 | Generate 100 synthetic patients with an LLM or Faker, incl. non-responder and warning-symptom cases | Sep 25 | T1.3 | Files validated against schema |
| T1.5 | M1 | Upload dataset to S3 | Sep 25 | T1.2, T1.4 | Files listed in bucket |
| T2.1 | M2 | Load records from S3 with LangChain loaders and chunk them | Sep 25 | T1.5 | Chunks per patient logged |
| T2.2 | M2 | Embed chunks and build ChromaDB (FAISS fallback) index | Sep 28 | T2.1 | Index persisted to disk and S3 |
| T2.3 | M2 | Build retriever filtered by patient ID; test 10 queries | Sep 28 | T2.2 | Correct patient's records returned |
| T3.1 | M3 | Patient Summary Agent: prompt + RAG call, structured output | Sep 28 | T2.3 | Summaries for 10 patients checked |
| T3.2 | M3 | Reminder Agent: personalized text, channel, send time, no clinical advice | Sep 29 | T3.1 | Reminders match each summary |
| T3.3 | M3 | Escalation Agent: rules + LLM risk flag (none / watch / escalate) | Sep 29 | T3.1 | Edge-case patients flagged correctly |
| T4.1 | M4 | Define LangGraph state and wire Summary → Reminder → Escalation | Sep 29 | T3.1–T3.3 | One run completes end to end |
| T4.2 | M4 | Add long-term memory: save reminders, responses, escalations to S3 and index | Sep 30 | T4.1 | Second run sees first run's history |
| T4.3 | M4 | Error handling, retries, and logging of every agent output | Sep 30 | T4.1 | Failed LLM call does not crash the run |
| T5.1 | M5 | Streamlit layout: patient list, run button, results panel | Sep 30 | T4.1 | Page loads with patient list |
| T5.2 | M5 | Show summary, reminder and escalation per patient; alerts view for staff | Oct 1 | T5.1, T4.2 | All three outputs visible |
| T5.3 | M5 | Simulate patient response input to test escalation | Oct 1 | T5.2 | Response changes the next run's flag |
| T6.1 | M6 | Launch EC2 (t3.medium), install Docker, open port 8501 to known IPs | Oct 1 | T1.2 | SSH and Docker work on instance |
| T6.2 | M6 | Store LLM API key in Secrets Manager or env vars | Oct 1 | T6.1 | No keys in code or image |
| T6.3 | M6 | Build and run container on EC2 with IAM role for S3 | Oct 2 | T6.1, T5.3 | App reachable at EC2 URL |
| T7.1 | M7 | End-to-end test on 20 patients; record accuracy of flags | Oct 2 | T6.3 | Test report written |
| T7.2 | M7 | README with setup steps; update architecture doc | Oct 2 | T6.3 | A new user can run it from README |
| T7.3 | M7 | Rehearse and deliver demo | Oct 3 | T7.1, T7.2 | Demo shown on deployed app |

## Risks and buffer

| Risk | Impact | Fallback |
| --- | --- | --- |
| LLM API rate limits or cost | Agents slow or blocked during testing | Cache responses; test on 10 patients, switch OpenAI ↔ Gemini |
| RAG returns wrong patient's data | Wrong summaries and reminders | Filter retriever by patient ID metadata (T2.3) |
| AWS setup delays (IAM, security groups) | Deployment slips past Oct 2 | Start T1.2 on day one; demo locally in Docker if EC2 fails |
| Agent integration takes longer than a day | M5 and M6 compressed | Use Sep 26–27 buffer; drop T5.3 before any core task |

If the plan slips, protect the core path first: data → RAG → three agents → workflow → deployed demo. Long-term memory polish and the response simulator are the first to cut.